## Sheet1
Legend: | Not Started | In Progress | Completed
Task | Start | Finish | Duration | 2018-08-28 | 2018-09-04 | 2018-09-11 | 2018-09-18 | 2018-09-25 | 2018-10-02 | 2018-10-09 | 2018-10-16 | 2018-10-23 | 2018-10-30 | 2018-11-06 | 2018-11-13 | 2018-11-20 | 2018-11-27 | 2018-12-04 | 2018-12-11 | 2018-12-18 | 2018-12-25 | 2019-01-01 | 2019-01-08 | 2019-01-15 | 2019-01-22 | 2019-01-29 | 2019-02-05 | 2019-02-12 | 2019-02-19 | 2019-02-26 | 2019-03-05 | 2019-03-12 | 2019-03-19 | 2019-03-26 | 2019-04-02 | 2019-04-09 | 2019-04-16 | 2019-04-23 | 2019-04-30 | 2019-05-07 | 2019-05-14 | 2019-05-21 | 2019-05-28 | 2019-06-04 | 2019-06-11 | 2019-06-18 | 2019-06-25 | 2019-07-02 | 2019-07-09 | 2019-07-16 | 2019-07-23 | 2019-07-30 | 2019-08-06 | 2019-08-13 | 2019-08-20 | 2019-08-27 | 2019-09-03 | 2019-09-10
Get Prjoect Assignment | 2018-08-28 | 2018-09-04 | 1 week
Meet Group | 2018-09-04 | 2018-09-07 | 3 days
Meet Advisor | 2018-09-11 | 2018-09-14 | 3 days
Set up Weekly Meeting Time/Place | 2018-09-14 | 2018-09-14 | 1 day
Weekly Progress Memo | 2018-09-12 | N/A | Continuous
Draft/Sign Level 1 Requirements | 2018-09-19 | 2018-09-20 | 1 day
Gantt Chart | 2018-09-19 |  | Continuous
Draft Backgroud | 2018-09-19 | 2018-09-28 | 9 days
Draft Specs | 2018-10-03 | 2018-10-12 | 9 days
Draft Alternatives | 2018-10-03 | 2018-10-12 | 9 days
Master Project Schedule Update | 2018-10-16
Course/Peer Review
Deliver Preliminary design presentation | 2018-10-17 | 2018-10-23 | 6 days
Failure Modes and Effects Analysis
Master Project Schedule Update
Critical Design Reviews
Draft Analysis and Manufacturing Plan Appendix
Final Report W/ Drawing/Manufacturing Etc
CDR Videos